: 20/05/2022

: tarique.ahmad@smartcontrols.in
: +91-8147167785

Date

Email 
Phone

To,

M/s JK Tyre & Industries Ltd

Hebbal Industrial Estate

Mysuru, Karnataka 570016

Kind Attention: Mr. Ashutosh Padhiary

Dear Sir,

Subject: Offer for SCADA Lite – Mixer Data Logging and Display Application

As per the discussions regarding the development of a SCADA Lite application for mixer data logging and display, equivalent to the ZSD (Kassel) current PVS application. The enclosed offer contains all the technical details of the proposed solution.

In case you need any further clarifications, please feel free to call us at any time convenient to you.

Thanking you and assuring you of our best attention at all times.

Yours truly,

Md Tarique Ahmad

Head of Sales, Digital Manufacturing

Smart Controls India Limited

Technical Offer

Offer Number	: XXX

Customer		: XXX ABC
End Customer	: XXX PQR

Project			: XXX MES

Table of Contents

2	Terms and Abbreviations	4

3	Basis Of Offer	5

3.1	Revision History	5

3.2	Functional Overview	5

3.3	Plant Location	5

3.4	Machine Details	5

4	Functional Details	5

4.1	Solution Architecture	5

4.2	IT Architecture	5

5	Scope Of Work	5

5.1	Key Deliverables	5

5.2	Scope Of Service	5

5.3	Scope Of Supply	5

5.3.1	Basis Of Supply	6

5.3.2	Bill Of Material	6

5.4	Scope of Work RACI	6

6	Project Management	6

6.1	Project Organization Structure	6

6.2	Project Governance	6

6.3	Project Phases and Deliverables	6

6.3.1	Requirement Freeze & Workshop	7

6.3.2	Functional Design Session	7

6.3.3	System Integrated Testing (SIT)	7

6.3.4	User Acceptance Testing (UAT)	8

6.3.5	Commissioning & Go Live	8

6.3.6	Rollout and Handover	8

6.4	Project Timelines	9

7	Project Understanding	9

7.1	General Assumptions	9

7.2	Project Assumptions	9

7.3	Customer Support	9

7.4	Exclusions	9

8	Change Request Procedure	10

8.1	Change in Scope Of Service	11

8.2	Change in Scope Of Supply	11

9	Acceptance Procedures	12

9.1	Notification of Deliverable Available Date	12

9.2	User Acceptance Tests	12

9.3	Inspection and Acceptance of Deliverables by Customer	12

# Terms and Abbreviations

| Terms | Definition |
| --- | --- |
| SCIL | Smart Controls India Ltd |
| CUSTOMER/ CUST | Zeppelin Systems GmbH |
| END CUSTOMER /ECST | Zeppelin Systems GmbH |
| BRD | Business Requirement Document |
| MES | Manufacturing Execution System |
| ERP | Enterprise resource planning |
| WMS | Warehouse Management System |
| PLC | Programmable Logic Controller |
| SCADA | Supervisory Control and Data Acquisition |
| RM | Raw Material |
| PO | Purchase order |
| GRN | Goods Received Note |
| OEM | Original Equipment Manufacturer |
| NCM | Non-Conformity Material |
| LIMS | Laboratory Information Management Systems |
| HMI | Human Machine Interface |
| BOM | Bill Of Material |
| OPC | Open Platform Communications |
| DB | Database |
| CMMS | Computerized Maintenance Management System |

# Basis Of Offer

This document is SCIL’s confidential and proprietary. SCIL provides this document to CUSTOMER with the understanding that its contents will be held in strict confidence and will not be duplicated or used in whole or in part for any purpose other than evaluation of this response, without prior written consent from SCIL.

This document reflects SCIL’s understanding of business needs and project requirements and was prepared based on the information available at that point in time. Any changes to these needs or requirements may require changes to any portion of this offer.

Any information related to potential future product functionality should not be construed as a guarantee or commitment on the part of SCIL to develop and/or deliver such functionality.

This information does not constitute an offer. Neither party will have any contractual commitment to the other until a definitive written contract has been negotiated and signed by the parties referring to this offer as technical and commercial scope.

## Revision History

R0

## Functional Overview

Smart Controls India Limited (SCIL) proposes to develop a lightweight, web-based application — SCADA Lite — for Zeppelin Systems GmbH, Kassel, based on the mutually agreed requirements. The application will replicate and extend the functionality of the current ZSD (Kassel) PVS application for mixer data logging and display, and will be owned and distributed by Zeppelin (Kassel) to their end customers.

Upon finalisation of requirements through a structured workshop and sign-off of the Functional Design Specification (FDS), SCIL will build, test, and deliver the complete application. The solution will provide real-time OPC UA communication with mixer PLCs, cyclic data logging to a relational database, and rich graphical trending for both online and historical batch data, along with process screen visualisation, role-based user management, and instance-based perpetual licensing.

Phase 1 – SCIL will develop and deliver the following functional scope as agreed with Zeppelin (Kassel): OPC UA communication with PLCs, configuration management (Mixers, Parameters, PLC Tags), cyclic data logging at up to 0.1-second frequency, online and historical graph/trend display with full customisation, process screen with real-time parameter values, and role-based user management.

Phase 2 – Subject to a separate requirement freeze and service order, SCIL will extend the application with Recipe Management, Production Order management, PLC transfer of recipes/orders, and batch report logging and display.

## Plant Location

Customer Plant: Zeppelin Systems GmbH, Kassel, Germany.

End Customer Plants: Rubber mixing plant sites operated by Zeppelin's global customer base.

The application is designed to be deployable at any site with network access, as it operates as a web application accessible remotely.

## Machine Details

The application targets rubber mixer machines (Banbury / Internal Mixers) equipped with Siemens PLCs that expose an OPC UA Server interface.

Key machine interface details:

• Communication Protocol: OPC UA (PLC acts as OPC UA Server; application acts as OPC UA Client)

• Configurable parameters: Mixer ID, PLC Tags, logging parameters

• Logging frequency: 1 second minimum; configurable down to 0.1 seconds

• Supported hardware: Medium-spec PCs/Laptops and Siemens Panel PCs running Windows OS

# Functional Details

## Solution Architecture

Figure 1: SCADA Lite – Solution Architecture (Source: SCADA Lite.pptx, Slide 1)

The SCADA Lite solution is structured across four functional layers:

1. Data Acquisition Layer

• Production Units / Rubber Mixer PLCs expose live process data via OPC UA Server.

• The Data Logger module (built on .NET OPC UA Client) connects to configured PLCs and cyclically logs parameter values to the database at configurable frequency (0.1 s – 1 s).

• Smartgate+ acts as the edge gateway bridging shopfloor OT network to IT network.

2. Data Processing Layer

• .NET-based Data Processing Services process raw logged data.

• Services handle: parameter condition evaluation, downtime detection, cycle time identification.

• Master data (Item List, BOM with cycle times, Plant/Area/Equipment hierarchy, Operator List) is maintained for contextual enrichment of raw data.

• API layer (.NET REST API) exposes processed data to the visualization layer.

3. Visualization Layer

• React JS web application provides the user interface, accessible via browser on any device on the plant network.

• Online (real-time) and history graph/trend display for configured parameters.

• Trend customisation: X/Y-axis span, channel selection, colour, zoom, cursor, legends.

• History query by Mixer, Date/Time, and Batch No./ID.

• Batch comparison (superimpose multiple batch trends on a single chart).

• Process screen showing real-time PLC tag values in grid format.

4. Web Hosting Layer

• Application backend and database are hosted on AWS cloud or on-premises server.

• Database: MS SQL Server / PostgreSQL.

• Flat file export capability for offline data exchange.

## IT Architecture

Technology Stack:

• Frontend:  React.js (web application – browser accessible)

• Backend:   .NET (REST API + Data Processing Services + OPC UA Client / Data Logger)

• Database:  Microsoft SQL Server (primary); PostgreSQL (alternative)

• Hosting:   AWS Cloud (or on-premises Windows Server)

Deployment & Compatibility:

• The UI is a web application accessible remotely from any device on the network.

• Application is compatible with recent Windows OS versions.

• Designed to run on medium-spec PCs/laptops and Siemens Panel PCs (lightweight footprint).

Networking:

• OT network: PLCs communicate via OPC UA to the Data Logger service.

• IT network: Data Logger, API, and database communicate over standard TCP/IP.

• Smartgate+ edge gateway bridges OT and IT network segments.

Security:

• Role-based User Management controls access to configuration, data, and administration.

• Instance-based perpetual licensing with hardware binding (Machine ID).

# Scope Of Work

## Key Deliverables

Phase 1 Deliverables:

1. SCADA Lite Application (Web) – React JS frontend with all Phase 1 UI screens

2. Data Logger Service – .NET OPC UA Client for cyclic data acquisition from PLCs

3. Data Processing Service – .NET backend for parameter processing and API

4. Database Schema & Setup – MS SQL Server / PostgreSQL with logging and master data tables

5. Configuration Module – Mixer, Parameter, and PLC Tag configuration interface

6. Graph/Trend Module – Online and historical trend display with full customisation

7. Process Screen – Real-time PLC tag value display in grid format

8. User Management Module – Role-based access control

9. Licensing Module – Instance-based perpetual license with hardware binding

10. Functional Design Specification (FDS) Document

11. Interface Control Design (ICD) Document (OPC UA interface)

12. User Manual / SOP Videos

13. SIT & UAT Sign-off Documents

Phase 2 Deliverables (scope to be finalised separately):

1. Recipe Management Module

2. Production Order Module

3. PLC Recipe/Order Transfer Interface

4. Batch Report Module (logging and display)

## Scope Of Service

Smart Controls India Limited (SCIL) will provide the following services:

• Requirement workshops and BRD creation

• Functional Design Specification (FDS) and Interface Control Design (ICD) documentation

• Full software development of SCADA Lite application (Phase 1 functional scope)

• OPC UA integration with mixer PLCs

• Database design, setup and master data configuration

• System Integration Testing (SIT) with demonstration to customer

• User Acceptance Testing (UAT) support and issue resolution

• Deployment to Production environment

• User manual and training video creation

• Hyper-care support post go-live

Delivery Model:

• Single-time development and release

• Source code ownership: Zeppelin (Kassel)

• Application distribution rights: Zeppelin (Kassel) to their customers

• Future bug fixes, support, and feature additions to be covered under separate service orders

## Scope Of Supply

### Basis Of Supply

The supply basis for this offer is as follows:

• SCIL supplies the developed software application (SCADA Lite) as a complete, tested deliverable.

• Source code is transferred to Zeppelin (Kassel) upon final acceptance.

• Customer (Zeppelin) is responsible for providing server/hosting infrastructure.

• Customer is responsible for OPC UA-enabled PLC infrastructure at site.

• Customer is responsible for OS, database software licenses, and antivirus on hosting servers.

• SCIL will recommend infrastructure specifications post FDS sign-off.

### Bill Of Material

Software / Service Items:

S.No | Item                                       | Qty | Unit   | Remarks

1    | SCADA Lite Application – Phase 1 Dev       |  1  | Lumpsum| Includes all Phase 1 modules

2    | OPC UA Client / Data Logger Service (.NET) |  1  | Lumpsum| Included in item 1

3    | React JS Web UI                            |  1  | Lumpsum| Included in item 1

4    | Database Schema & Configuration            |  1  | Lumpsum| Included in item 1

5    | FDS + ICD Documentation                   |  1  | Lumpsum| Project deliverable

6    | User Manual / SOP Videos                  |  1  | Lumpsum| Project deliverable

7    | Project Management                        |  1  | Lumpsum| Throughout project lifecycle

Note: Commercial pricing is detailed in Annexure A – Commercial Scope.

# Roles And Responsibilities

| RACI Terms |  |  |
| --- | --- | --- |
| R | Responsible | Team who performs the activity. |
| A | Accountable | Team who should answer for the success/failure/quality and timeliness of action. |
| C | Consulted | Team who must be consulted before the action is performed. |
| I | Informed | Team who must be informed after the action is performed. |

## Overall RACI

| Area | Scope | Details | Owner | Remarks |
| --- | --- | --- | --- | --- |
| Infrastructure | Supply | Infrastructure For MES Usage |  | Specification recommendation by SCIL. Actual estimation shall be evaluated post FDS Sign off. |
|  |  | SIT, UAT and PROD | CUST |  |
|  | Supply | Infrastructure During Implementation |  |  |
|  |  | DEV | CUST |  |
|  | Supply | Network Components |  | Recommendation by SCIL. |
|  |  | Shopfloor OT and IT Network | CUST |  |
|  | Supply | Scanner, Printer, IPC, PDA |  | Actual estimation shall be evaluated post FDS Sign off. |
|  |  | Shopfloor MES HMI | CUST |  |
|  | Supply | Infrastructure Software License ( Database, OS, Antivirus, Monitoring tool etc) | CUST | Specification recommendation by SCIL. Database Actual estimation shall be evaluated post FDS Sign off. |
|  |  | PROD, SIT, UAT Servers | CUST |  |
|  |  | DEV | SCIL |  |
| Application | Supply | Siemens Software License ( EXPR , OPIN, RDNL, MIO etc) |  | Actual load and license shall be reevaluated post FDS Sign off. |
|  |  | PROD, SIT, UAT Servers | SCIL |  |
|  |  | DEV |  |  |
|  | Supply | Siemens Other License ( Curing SCADA, MES SCADA etc) | SCIL |  |
|  |  | PROD, SIT, UAT Servers |  |  |
|  |  | DEV | SCIL |  |
|  | Service | Layer 2 - SCADA Software Implementation |  |  |
|  |  | TBM SCADA, CURING SCADA, PLANTWIDE SCADA | SCIL |  |
|  | Service | Layer 3 - MoM Software Implementation |  |  |
|  |  | MES, LIMS | SCIL |  |
|  | Service | 3rd Party Integration (ERP, WMS, ASRS etc) |  |  |
|  |  | Integration and Development | CUST |  |

## Scope of Work RACI

| S.No | Phase | Area | Activity | SCIL | CUST | ECST |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Requirement | Workshop | Requirement gathering workshops arrangement with all Stakeholders. | R | A | C |
| 2 | Requirement | Documentation | Business Requirement Document creation. | R | C | I |
| 3 | Requirement | Requirement Checkpoint. | Business Requirement Document Sign Off | C | A | R |
| 4 | Requirement | Documentation | User Acceptance Criteria creation | R | C | A |
| 5 | Designing | Workshop | Conference room pilot with process owners/ business heads on need basis. | R | A | C |
| 6 | Designing | Documentation | Data requirements and availability of all application and interfaces | C | A | R |
| 7 | Designing | Infrastructure | Server sizing & specification recommendation. | C | C | R |
| 8 | Designing | Hardware | AIDC (Scanner, printer, PDA etc ) specification recommendation . | C | C | R |
| 9 | Designing | Application | Overall Solution architecture document creation. | R | A | C |
| 10 | Designing | Application | Infrastructure architecture document creation. | R | A | C |
| 11 | Designing | Application | Database requirements & specifications | C | A | R |
| 12 | Designing | Documentation | Functional design documentation. | R | A | C |
| 13 | Designing | Documentation | Interface Control design documentation | R | A | C |
| 14 | Designing | Management | Cordination with all OEM's for disucssion and follow ICD. | C | C | R |
| 15 | Designing | Integration Checkpoint. | Interface Control design Sign Off. | C | A | R |
| 16 | Designing | Solution Checkpoint. | Functional design Sign Off. | C | A | R |
| 17 | Designing | Acceptance Checkpoint. | User Acceptance Criteria Sign Off. | C | A | R |
| 18 | Designing | Documentation | Traceability matrix against Requirement IDs | R | A | I |
| 19 | Development | Data | Master and transactional data template. | R | C | I |
| 20 | Development | Data | Master and transactional data availability in template. | I | C | R |
| 21 | Development | Data | Master Data upload. | R | C | I |
| 22 | SIT | Management | Readiness of all OEM's interfaces for Integration testing. | I | C | R |
| 23 | SIT | Demo | Demo of possible feature. | R | A | C |
| 24 | SIT | Demo | Demo feedback and acceptance. | R | A | C |
| 25 | Testing | Application | User Acceptance Criteria Testing | C | A | R |
| 26 | Testing | Documentation | UAT test plan | R | A | C |
| 27 | Testing | Documentation | UAT Sign off | C | A | R |
| 28 | Commissioning | Application | MES Products installation. | R | A | I |
| 29 | Commissioning | Infrastructure | VM, Database and other 3rd party application installation. | C | C | R |
| 30 | Commissioning | Infrastructure | Server mounting, Storage configuration, OS, Antivirus, Network Readiness in Datacentre. | C | C | R |
| 31 | Commissioning | Infrastructure | Backup Software if any | C | C | R |
| 32 | Commissioning | Documentation | SOP and user manual | R | C | I |
| 33 | Commissioning | Infrastructure | Infrastructure, Database, Backup monitoring tools installation. | I | C | R |
| 34 | Hyper Care | Infrastructure | VM/Server Monitoring - Manually monitor the availability and performance of the Virtual Machines using OEM provided management tools at periodic intervals. | I | C | R |
| 35 | Hyper Care | Application | DB Monitoring - Manually monitor the availability of the databases using OEM provided management tools at periodic intervals | R | A | I |
| 36 | Hyper Care | Infrastructure | Backup Monitoring - Monitor the failed backup jobs Backup software console at periodic intervals | I | C | R |
| 37 | Hyper Care | Application | Application Monitoring : Monitor the availability of applications | R | A | I |
| 38 | Hyper Care | Application | Performance Maintenance - configuration changes, clean-up environment, identify inefficient SQL queries, Perform scheduled database start-up/shutdown, Database recovery | R | A | I |
| 39 | Hyper Care | Application | DB Structural Maintenance - Table space, disk space, and temporary space management, Database object structural management, Maintain physical database layout | R | A | I |
| 40 | Hyper Care | Infrastructure | Network Monitoring System installation | I | C | R |
| 41 | Hyper Care | Infrastructure | VM, Server, OS, Antivirus, other software maintenance | I | C | R |

# Project Management

## Project Organization Structure

## Project Governance

## Project Phases and Deliverables

### Requirement Freeze & Workshop

Smart Controls Team to organize workshop to collect, understand, review, finalize and fine tune the software and hardware requirements. The workshop could be conducted online or at customer site.

Customer shall align all the required experts and resources during workshop to clarify and explain the requirements in detail. Customer shall arrange all 3rd party experts for the interface discussion if required to be integrated with required software.
Customer shall provide the User Acceptance Criteria (UAC) to Smart Controls for final acceptance of agreed requirements.

Smart Controls to create a final Business Requirement Document (BRD) at the end of the workshop to be considered as the final deliverables. Any deviation in requirement from the basis of the offer to follow “Change Request Procedure “section mentioned in this document.

Smart Controls and Customer shall calibrate on the scope of supply and service post requirement clarity and definition.

As per the requirement clarification and detailing, the final scope of supply and service, project timeline, Solution Architecture, IT Architecture to be re-evaluated. Any required modification to be mutually discussed and considered for project implementation.

Finalized BRD to be signed off by both the parties.

### Functional Design Session

Smart Controls team to design the solution as per the signed off BRD. The solution design to cover the functional details of requirements and process flow of solution.

Smart Controls shall engage customer as and when needed with to clarify and design the solution. Customer shall align all required stakeholder to define and contribute to the solution designing process.

Smart Controls must document all the solution design in final Functional Design Specification (FDS) Document explaining the to be developed/configured functional design of the software.

Smart Controls must document the required interfaces with any 3rd party software as per the requirement and solution in Interface Control Design (ICD) Document.

At the end of Functional Design session, the final FDS and ICD must be signed off with both the parties (Smart Controls and Customer) before the development is proceeded. Customer shall provide the User Acceptance criteria sign off for final acceptance of agreed requirements and solution.

### System Integrated Testing (SIT)

During the software build and development Smart Controls team to perform the system integrate testing with all the modules developed and integrated with 3rd party system if any.

The developed modules will be deployed in SIT Server for demonstrations.

Smart Controls shall demonstrate the developed modules of the solution with integrating with 3rd party software if any.

Customer shall align all required stakeholder to understand and provide comments on developed modules. At the end of SIT, the modules will be demoed, and comments will be recorded.

### User Acceptance Testing (UAT)

After completion of SIT, the software will be deployed in UAT Server for final acceptance testing. All the required machines/3rd party software will be integrated with as like Production environment.

Smart Controls must deploy all the modules and integrate with actual devices. Customer shall perform system validation, executing User Acceptance Criteria to validate requirements delivery and system functionality.

Smart Controls will respond to issues and concerns raised during the validation stage.

Customer shall align all required stakeholder/Hardware/Server to perform the final test and accept the developed modules against the UAC.

At the end of UAT, the UAT will be Signed off by both parties and system will be accepted to go live.

### Commissioning & Go Live

After completion of UAT, the software will be deployed in Production Server.

All the required machines/3rd party software will be integrated as per UAT sign off. Smart Controls must deploy all the modules and integrate with devices/software. Smart Controls will provide the user manual videos to the end user to understand the system for usability.

Customer shall align all required stakeholder/Hardware/Server to deploy the solution on production server.

At the end of Commissioning and Go Live, the developed modules will be available to be used for respected end user.

### Rollout and Handover

Once the modules are commissioned and live in production server, the software will be under hyper care by Project team. In this hyper care duration system will be monitored for performance, functionality and bugs. Any bugs /improvement points identified will be fixed/improved by the project team.

Smart Controls will provide the all-user manual videos to the end user to understand the complete system for usability.

At the end of Rollout and Handover, the developed modules will be handed over to customer with required functional training videos.

## Project Timelines

The project timeline will be mutually agreed between Zeppelin (Kassel) and Smart Controls at the project kick-off, based on the contractual schedule. Indicative phase durations are:

Phase                              | Indicative Duration

Requirement Freeze & Workshop      | 2 weeks

Functional Design Session          | 3 weeks

Development & Build                | 8 weeks

System Integration Testing (SIT)   | 2 weeks

User Acceptance Testing (UAT)      | 2 weeks

Commissioning & Go Live            | 1 week

Rollout, Handover & Hyper-care     | 4 weeks

Total Indicative Duration: ~22 weeks from project kick-off (subject to BRD and FDS sign-off timelines).

# Project Understanding

## General Assumptions

- The language for project, training, operator’s documentation, and user interface will be English.

- Customer is responsible to perform system validation, including developing and executing test cases (User Acceptance Test) to validate requirements and system functionality. Smart Controls will respond to issues and concerns raised during the validation stage.

- The overall project schedule shall be mutually agreed between Customer and Smart Controls at the beginning of the project, based on the contractual project schedule.

- Change request development will be done in Smart Controls premises and commissioning will be done on customer site.

- The complete job will be done remotely and onsite as per the project phase and SCIL decision for project completion.

- If Customer not able to supply any required facilities, resources, assistance or information in a timely manner, corresponding additional man days to complete these activities will be charged to customer on a time and materials basis using SmartControls standard rates in effect from time to time for any resulting additional work or waiting time.

## Project Assumptions

• Zeppelin (Kassel) will assign a dedicated project coordinator for requirement gathering and UAT.

• PLC OPC UA Server configuration at the machine side is in scope of Zeppelin / End Customer.

• OPC UA tag list and PLC structure will be provided by Zeppelin prior to FDS.

• Ricardo Klement from ZSD will provide UI/UX design wireframes following NAMiQ standards.

• Server/hosting infrastructure (AWS or on-premises) will be procured and made available by Zeppelin prior to UAT phase.

• MS SQL Server or PostgreSQL license will be provided by Zeppelin.

• Stable network connectivity between the application server and PLC OPC UA server is assumed.

## Customer Support

Zeppelin (Kassel) shall provide the following support during the project:

• Access to mixer machines and PLCs for OPC UA tag verification during SIT/UAT.

• Availability of subject matter experts (process engineers, IT team) during workshops and FDS.

• Timely sign-offs on BRD, FDS, ICD, and UAT to avoid project delays.

• Provision of server infrastructure and network access for SIT, UAT, and Production environments.

• UI/UX wireframes as per NAMiQ design standards (by Ricardo Klement, ZSD).

## Exclusions

The following are excluded from the scope of Service of Smart Controls unless, otherwise explicitly mentioned in this document.

- Materials and activities on field devices and equipment (e.g., PLCs modification). Or modification of existing equipment for any process automation.

- Any hardware/supply/service item not explicitly mentioned in this document.

# Change Request Procedure

Any deviation requested in this proposal OR during implementation OR post implementation phase in project will follow the below mentioned procedure. The standard change process can be graphically represented as follows:

This change process covers all major/minor changes. All change orders are submitted by the project management and quantified with respect to budget and time.

Both project managers must approve the change before the described activity may be performed. If no agreement between the project managers can be achieved, the change is not accepted. Each project manager can invoke the Steering Board for further decision.

Should any assumption set out or referred to in the proposal prove to be invalid or should fail to carry out any of your obligations under the proposal, Smart Controls will be entitled to equitable adjustments to the Services and to charge customer on a time and materials basis using Smart Controls standard rates in effect from time to time for any resulting additional work or waiting time.

## Change in Scope Of Service

| Stages | Responsible | Dependency | Action |
| --- | --- | --- | --- |
| Change Request | Customer | CR Approval. | Customer to document the required change in detail and provide all related master data and prerequisites. |
| Solutioning | Smart Controls | Customer to provide complete requirement details and all related prerequisites. | Smart Controls to perform impact analysis, code analysis and design the solution. The solution to be discussed and mutually agreed with Customer. |
| Building | Smart Controls | Customer to provide the acceptance criteria for the change. | Smart Controls to build the solution and preform unit testing and check acceptance criteria shared by Customer. |
| UAT | Customer | Smart Controls to deploy the solution on UAT Server. | Customer to test the solution in UAT server, perform impact and risk analysis and provide acceptance. |
| PROD | Smart Controls | Customer to provide the UAT acceptance. | Smart Controls to deploy the solution in PROD Server. |
| PROD | Smart Controls | Smart Controls to complete deployment. | Customer performs the acceptance testing in PROD Server. |

## Change in Scope Of Supply

| Stages | Responsible | Dependency | Action |
| --- | --- | --- | --- |
| Change Request | Customer | CR Approval. | Customer to document the required change in detail and provide related hardware specification details. |
| Solutioning | Smart Controls | Customer to provide complete requirement details and all related prerequisites. | Smart Controls to perform impact analysis and redesign the solution if needed. The solution/change/impact to be discussed and mutually agreed with Customer. |
| Procurement & Readiness | Smart Controls | Smart Controls and Customer to mutually agree to the change impact. | Smart Controls to procure the material as per CR and preform the required configurations on the hardware as per mutually agreed scope of work for the hardware. |
| UAT | Customer | Smart Controls to deploy the hardware on UAT Server. | Customer to test the hardware in UAT server and provide acceptance. |
| PROD | Smart Controls | Customer to provide the UAT acceptance. | Smart Controls to commission the hardware in PROD Server and performs the final acceptance testing. |

# Acceptance Procedures

## Notification of Deliverable Available Date

The approval of documents is given in writing; for other delivery units (e.g., system and training) an approval report is prepared. Acceptance will be confirmed in writing. The same process will be applicable for each deliverable of each milestone. Smart Controls is responsible to give Customer notification of the date when the deliverable as listed in project deliverables section will be available for acceptance by the Customer

## User Acceptance Tests

For the description of test cases, a form will be provided which is commonly agreed by the project manager from Smart Controls and the customer will be used.

## Inspection and Acceptance of Deliverables by Customer

Customer will notify Smart Controls in writing within five (5) working days following receipt of any milestone related deliverable for which Smart Controls has responsibility for delivery, if the deliverable fails to meet the acceptance criteria (if any) set out above. This notice shall state in reasonable detail and in a consolidated manner the reasons for a deliverable failing to meet such criteria.

Acceptance by the Customer shall not be unreasonably withheld. The passage of five (5) working days without notice of non-acceptance following delivery to Customer or the productive use by Customer of such deliverable shall constitute acceptance by the Customer.

If the notice of non-acceptance is not sufficiently detailed to allow Smart Controls to determine why such deliverable is unacceptable, Smart Controls may request in writing that the Customer provides sufficient additional information. The passage of five (5) working days from the date of such request without the provision of such additional information shall constitute acceptance of such deliverable by the Customer.

Smart Controls shall either rework such deliverable within fifteen (15) days after receipt of sufficient notice or present the Customer with a plan to rework the deliverable within a period of time that is reasonable under the circumstances.

Where the Scope of work does not set out acceptance criteria for any deliverable for which Smart Controls has responsibility for delivery, the deliverable will be deemed accepted on delivery to the Customer.

The project is completed if all deliverables as described are delivered to the Customer and accepted by the Customer via a formal Acceptance Document/email.

# Ownership Of Deliverables

- Pre-existing Software and Technology. Each party will retain all rights in any software, ideas, concepts, know-how, development tools, techniques or any other proprietary material or information that it owned or developed prior to the inception of a professional services project or acquired or developed thereafter without reference to or use of the intellectual property of the other party.

- Third Party Software and Technology. All software and technology that is licensed by a party from a third-party vendor will be and remain the property of such vendor.

- Deliverables Based on SmartControls Software and Technology. Subject to any third-party rights or restrictions, SmartControls will own all intellectual property rights in or related to all deliverables that are developed and delivered by SmartControls, provided that they consist of pre-existing SmartControls software or SmartControls software development tools, modifications thereto developed as part of the Services or works derived from pre-existing SmartControls software or SmartControls Tools developed as part of the Services.

- Deliverables Based on Customer’s Software and Technology. Subject to any third-party rights or restrictions, Customer shall own all intellectual property rights in or related to any deliverables that do not constitute pre-existing SmartControls software, SmartControls Tools, or modifications thereto or works derived therefrom, that are developed as part of the Services.

- The Services provided hereunder shall not constitute “works made for hire” under any applicable copyright laws. Ownership of work in progress under a Scope of Work shall remain with SmartControls until such time as title to a Deliverable transfer, if at all, in accordance with the signed Agreement.

- No License to Intellectual Property of the Other Party: No licenses will be deemed to have been granted by either party to any of its patents, copyrights, trade secrets or other intellectual property except as otherwise expressly provided in the Agreement. SmartControls will be free to use the ideas, concepts, methodologies, processes and know-how that are developed or created in the course of performing the Services provided that SmartControls does not use, or make reference to, the intellectual property or proprietary information of Customer.

# Annexure A – Commercial Scope

-----To be included ---